## Instructions
Roadmap — Transformation Risks Upload Template
1
Drives the 'Risks & Mitigation' governance section on the Transformation Roadmap page.
Each row is a programme, technical, resource, compliance, commercial, or vendor risk.
Status values: Open ¦ Mitigating ¦ Closed. Allowed values are listed in the Instructions sheet.
Likelihood / Impact / Rating values: High ¦ Med ¦ Low. Allowed values are listed in the Instructions sheet.
Category values: Program ¦ Technical ¦ Resource ¦ Compliance ¦ Commercial ¦ Vendor. Allowed values are listed in the Instructions sheet.
1
Sheets in this workbook:
• Risks — 10 columns, writes to table "roadmap_risks"
1
Rules:
• The first row of every sheet is the header row. Do not rename or reorder columns.
• Each sheet is loaded into its own table. Existing rows are replaced on upload.
• Required cells must not be empty. Optional cells may be left blank.
• The entire upload is atomic: if any row fails validation, NOTHING is written and the database stays as it was.
• Save as .xlsx (Excel Workbook) and upload via Administration → this dataset's tab.

## Risks
Title | Category | Likelihood | Impact | Rating | Owner | Mitigation Action | Status | Raised Date | Notes
AIOps Approval and Tooling Access Delay | Program | High | High | High | Horizon Platform Operations / IBM AIOps Lead | Secure formal approval for AIOps enablement, data feeds, monitoring integrations, and access to observability platforms. Start with a controlled pilot for 2–3 priority application groups and use incident reduction / MTTR baseline to confirm value before scaling. | Mitigating | 2026-06-23 | Decision needed to unlock automation backlog, telemetry onboarding, and operational KPI tracking.
Limited Stakeholder Acceptance for Agile Ways of Working | Program | Med | High | High | Horizon Business Product Owners / IBM Delivery Lead | Identify selected projects for Agile adoption, agree sprint ceremonies, establish business product owner participation, and use a 6–8 week pilot to demonstrate speed, transparency, and backlog discipline before expanding across all towers. | Open | 2026-06-23 | Risk is highest where business teams are used to monthly governance and fixed-scope delivery.
CareOps360 Governance Tab Deployment Readiness | Technical | Med | High | High | Horizon Digital Governance Owner / IBM Portal Team | Finalize hosting, authentication, data refresh process, role-based access, and weekly content ownership. Deploy the governance tab first with roadmap, risks, milestones, actions, and KPI sections covering the highest-value monthly deck content. | Mitigating | 2026-06-23 | Portal should simulate 50–60% of high-value governance deck content and reduce manual deck production.
Product Model Finalization and Domain Ownership Delay | Program | High | High | High | Horizon IT Leadership / IBM Transformation Lead | Confirm product domains, product owners, POD alignment, decision rights, and funding ownership. Conduct leadership review to approve the model and publish a product taxonomy with mapping to applications, services, and transformation initiatives. | Mitigating | 2026-06-23 | Without final product model, POD transformation and product-based talent view may remain conceptual.
Transformation Initiative Funding Not Approved on Time | Commercial | High | High | High | Horizon Finance / Transformation Steering Committee | Create a prioritized initiative backlog with business case, investment ask, benefits, timing, and delivery dependency. Seek phased funding approval for quick-win initiatives while larger transformation items go through governance. | Open | 2026-06-23 | Funding alignment is required for AIOps, CareOps360 expansion, Agile enablement, and POD model execution.
Insufficient Horizon SME Availability for Workshops and Decision Gates | Resource | Med | High | High | Horizon Application Owners / IBM Program Manager | Lock recurring SME windows, publish workshop calendar, pre-read materials, and decision logs. Escalate missed decision gates through operating committee with clear impact on roadmap timelines and value realization. | Mitigating | 2026-06-23 | Applies to product model, capability maturity, Agile pilot selection, and application governance decisions.
Data Quality and Integration Gaps in Governance Reporting | Technical | Med | Med | Med | Horizon Data Owners / IBM Reporting Lead | Define system-of-record for milestones, risks, actions, financials, tickets, and application inventory. Standardize weekly data refresh and validation checks before publishing CareOps360 governance dashboards. | Open | 2026-06-23 | Poor data quality can reduce trust in CareOps360 and force continued reliance on manual monthly decks.
Change Resistance to POD Transformation and Product-Based Talent View | Resource | Med | High | High | Horizon HR / IT Leadership / IBM Enablement Lead | Build a change plan with leader messaging, role clarity, skill mapping, enablement sessions, and transition support. Start with selected domains and use before/after operational metrics to demonstrate benefit. | Open | 2026-06-23 | Risk includes concerns around role changes, reporting lines, accountability, and new operating rhythm.
Security, Compliance, and Access Review Delays for Portal and AIOps | Compliance | Med | High | High | Horizon Security / Compliance / IBM Security Architect | Initiate security review early for CareOps360, telemetry integrations, access roles, audit logging, and data retention. Use least-privilege access and avoid storing restricted production data unless approved. | Mitigating | 2026-06-23 | Important for HIPAA-sensitive operating environment and enterprise governance expectations.
Benefits Realization Not Tracked Against Transformation Commitments | Program | Med | High | High | Horizon Transformation Office / IBM Value Realization Lead | Define baseline, target benefits, KPI owners, measurement cadence, and value sign-off process. Add a value realization dashboard in CareOps360 showing initiative status, benefit category, realized value, and blockers. | Open | 2026-06-23 | Needed to support transformation acceptance, funding continuation, and executive confidence.