## Dashboard
Horizon AMS Reinvention — First 180 Days Transition Dashboard
Plan start: July 1, 2026 ¦ Scope: Transition, QE, AIOps, CareOps360, Agile/Product model ¦ Update % Complete / Status in Master Plan to refresh tracking views
Total Tasks | 99
Completed | 0
At Risk / Blocked | 0
Avg % Complete | 0%
Critical/High Tasks | 99
Workstream | Tasks | Completed | In Progress | At Risk/Blocked | Avg % Complete | Phase | Tasks | Completed
Overall Transition | 19 | 0 | 0 | 0 | 0% | 0-30 Foundation | 36 | 0
Quality Engineering | 21 | 0 | 0 | 0 | 0% | 31-60 Production Ready | 19 | 0
AIOps Implementation | 20 | 0 | 0 | 0 | 0% | 61-90 Standardize & Integrate | 19 | 0
CareOps360 | 20 | 0 | 0 | 0 | 0% | 91-180 Scale & Optimize | 25 | 0
Agile Product Model | 19 | 0 | 0 | 0 | 0%
Month | Milestones Ending | Tasks Starting | Cumulative Tasks Ending |  |  | Workstream | Jul | Aug | Sep | Oct | Nov | Dec
2026-07-01 | 31 | 42 | 31 |  |  | Overall Transition | 10 | 6 | 4 | 3 | 3 | 2
2026-08-01 | 22 | 19 | 53 |  |  | Quality Engineering | 8 | 8 | 7 | 3 | 4 | 3
2026-09-01 | 18 | 18 | 71 |  |  | AIOps Implementation | 8 | 5 | 5 | 4 | 4 | 3
2026-10-01 | 8 | 10 | 79 |  |  | CareOps360 | 8 | 6 | 5 | 4 | 3 | 2
2026-11-01 | 8 | 8 | 87 |  |  | Agile Product Model | 8 | 5 | 5 | 4 | 4 | 2
2026-12-01 | 12 | 2 | 99
Source / planning assumptions: Plan is derived from the Horizon AMS Reinvention Round 2 Orals deck and assumes a July 1, 2026 transition start. Dates, owners and dependencies should be finalized with Horizon during transition mobilization. Update task Status and % Complete in the Master Plan to refresh dashboard formulas.
Formulas:
Tasks = COUNTIFS('180D Master Plan'!H:H,">="&[Workstream],'180D Master Plan'!H:H,"<"&EDATE([Workstream],1))
Completed = COUNTIFS('180D Master Plan'!G:G,">="&[Workstream],'180D Master Plan'!G:G,"<"&EDATE([Workstream],1))
In Progress = COUNTIF('180D Master Plan'!H:H,"<"&EDATE([Workstream],1))

## 180D Master Plan
ID | Workstream | Phase | Task / Activity | IBM Owner | Horizon Owner | Start Date | End Date | Duration Days | Dependencies | Deliverable / Milestone | Success Metric | Status | Priority | % Complete | RAG | Notes
OVE-01 | Overall Transition | 0-30 Foundation | Confirm transition charter, scope, governance cadence and 180-day success criteria | IBM Transformation Lead | Horizon Executive Sponsor | 46204 | 46206 | 3 |  | Signed transition charter | Steering cadence active; 180-day KPIs approved | Not Started | High | 0 | Green
OVE-02 | Overall Transition | 0-30 Foundation | Establish integrated transition command center and daily/weekly operating rhythm | IBM Delivery Lead | Horizon PMO | 46204 | 46208 | 5 | TR-01 | Transition command center | Daily standups, weekly operating review, escalation path live | Not Started | High | 0 | Green
OVE-03 | Overall Transition | 0-30 Foundation | Validate in-scope applications, services, SLAs, owners and incumbent knowledge repositories | IBM Transition Manager | Horizon App Owners | 46207 | 46213 | 7 | TR-01 | Validated inventory and SLA baseline | 100% critical services mapped | Not Started | High | 0 | Green
OVE-04 | Overall Transition | 0-30 Foundation | Complete access, environment, tooling and onboarding plan for IBM transition resources | IBM Delivery Lead | Horizon Security / ITSM | 46207 | 46216 | 10 | TR-01 | Access tracker and onboarding plan | Access SLA agreed; blockers visible | Not Started | High | 0 | Green
OVE-05 | Overall Transition | 0-30 Foundation | Execute knowledge transfer wave 1 for critical applications and operations processes | IBM App Leads | Horizon SMEs | 46211 | 46220 | 10 | TR-03;TR-04 | KT wave 1 artifacts | Critical apps have runbooks, support matrix and SME sign-off | Not Started | High | 0 | Green
OVE-06 | Overall Transition | 0-30 Foundation | Baseline current incident, request, change, defect and deployment metrics | IBM Service Delivery Manager | Horizon ITSM Lead | 46215 | 46226 | 12 | TR-03 | Operational baseline dashboard | MTTR, ticket volume, backlog aging and SLA baseline captured | Not Started | High | 0 | Green
OVE-07 | Overall Transition | 0-30 Foundation | Map AMS towers to initial product/value-stream POD structure | IBM Product Engineering Lead | Horizon Product Owners | 46218 | 46227 | 10 | TR-03 | Initial POD alignment map | Applications mapped to domains/value streams | Not Started | High | 0 | Green
OVE-08 | Overall Transition | 0-30 Foundation | Finalize interim run/support model and hypercare approach for first 60 days | IBM Delivery Lead | Horizon Operations Lead | 46225 | 46234 | 10 | TR-02;TR-05 | Run support model | No service disruption; escalation path tested | Not Started | High | 0 | Green
OVE-09 | Overall Transition | 31-60 Production Ready | Stabilize delivery governance, integrated risk log, dependency log and executive reporting | IBM Transformation Office | Horizon PMO | 46234 | 46248 | 15 | TR-02;TR-06 | Governance pack | Weekly reporting with risks, dependencies and KPIs | Not Started | High | 0 | Green
OVE-10 | Overall Transition | 31-60 Production Ready | Complete knowledge transfer wave 2 for business-critical and medium-critical applications | IBM App Leads | Horizon SMEs | 46234 | 46253 | 20 | TR-05 | KT wave 2 artifacts | >85% KT completion; gaps documented | Not Started | High | 0 | Green
OVE-11 | Overall Transition | 31-60 Production Ready | Transition service delivery accountability to IBM POD/service leads with shadow-to-reverse-shadow plan | IBM Delivery Lead | Horizon Operations Lead | 46243 | 46257 | 15 | TR-08;TR-10 | Service transition cutover checklist | POD leads own daily execution | Not Started | High | 0 | Green
OVE-12 | Overall Transition | 31-60 Production Ready | Implement SLA/CSL reporting pack aligned to business KPIs and operational metrics | IBM Service Delivery Manager | Horizon ITSM Lead | 46248 | 46262 | 15 | TR-06;TR-09 | SLA/CSL dashboard | Business KPIs and critical service levels visible monthly | Not Started | High | 0 | Green
OVE-13 | Overall Transition | 61-90 Standardize & Integrate | Optimize support model based on 60-day learnings and adjust staffing by product demand | IBM Delivery Lead | Horizon Product Owners | 46264 | 46283 | 20 | TR-11;TR-12 | Optimized support model | Backlog and incident queues balanced by domain | Not Started | High | 0 | Green
OVE-14 | Overall Transition | 61-90 Standardize & Integrate | Launch transformation backlog intake for tech debt, ticket reduction and strategic initiatives | IBM Transformation Lead | Horizon Portfolio Lead | 46264 | 46288 | 25 | TR-09 | Transformation backlog | Initiatives scored by value, risk and feasibility | Not Started | High | 0 | Green
OVE-15 | Overall Transition | 61-90 Standardize & Integrate | Run first value realization review and confirm reinvestment / modernization candidates | IBM Transformation Lead | Horizon Executive Sponsor | 46278 | 46292 | 15 | TR-14 | Value review readout | Savings and value opportunities quantified | Not Started | High | 0 | Green
OVE-16 | Overall Transition | 91-180 Scale & Optimize | Scale transition governance into product-centric monthly/quarterly operating model | IBM Transformation Office | Horizon PMO | 46294 | 46323 | 30 | TR-13;TR-15 | Quarterly operating model | Product roadmap, KPI, financial and value governance running | Not Started | High | 0 | Green
OVE-17 | Overall Transition | 91-180 Scale & Optimize | Implement continuous improvement loop for incidents, RCA, automation and knowledge updates | IBM SRE / Ops Lead | Horizon Operations Lead | 46303 | 46347 | 45 | TR-13 | Continuous improvement backlog | Repeat incidents trend down; RCA actions tracked | Not Started | High | 0 | Green
OVE-18 | Overall Transition | 91-180 Scale & Optimize | Finalize Year-1 transformation roadmap refresh using 180-day operating data | IBM Transformation Lead | Horizon Executive Sponsor | 46323 | 46367 | 45 | TR-15;TR-17 | Year-1 roadmap refresh | Funded roadmap with near-term priorities | Not Started | High | 0 | Green
OVE-19 | Overall Transition | 91-180 Scale & Optimize | Execute 180-day transition health assessment and transition-to-steady-state acceptance | IBM Delivery Lead | Horizon Executive Sponsor | 46353 | 46382 | 30 | TR-16;TR-18 | 180-day acceptance report | Steady-state acceptance and remaining actions signed off | Not Started | High | 0 | Green
QUA-01 | Quality Engineering | 0-30 Foundation | [QE] Mobilize QE transition team, clarify testing scope and confirm QE governance | IBM QE Lead | Horizon QA Lead | 46204 | 46208 | 5 |  | QE mobilization plan | QE governance and owners confirmed | Not Started | High | 0 | Green
QUA-02 | Quality Engineering | 0-30 Foundation | [QE] Assess current test assets, automation coverage, defect leakage and regression cycle health | IBM QE Architect | Horizon QA Lead | 46207 | 46214 | 8 | QUA-01 | QE maturity assessment | Automation baseline, test pack gaps and defect trends documented | Not Started | High | 0 | Green
QUA-03 | Quality Engineering | 0-30 Foundation | [QE] Define end-to-end QE strategy: shift-left, BDD/TDD, SIT, UAT support and non-functional testing | IBM QE Lead | Horizon QA Lead | 46211 | 46220 | 10 | QUA-02 | QE strategy and playbook | Standardized test lifecycle agreed | Not Started | High | 0 | Green
QUA-04 | Quality Engineering | 0-30 Foundation | [QE] Inventory critical business flows and identify regression pack rationalization opportunities | IBM QE Analyst | Horizon Business SMEs | 46215 | 46226 | 12 | QUA-02 | Critical flow catalog | Top flows prioritized by business risk | Not Started | High | 0 | Green
QUA-05 | Quality Engineering | 0-30 Foundation | [QE] Establish requirement-to-test traceability model in Jira/GitHub/toolchain | IBM QE Architect | Horizon Tooling Lead | 46219 | 46233 | 15 | QUA-03 | Traceability model | Stories, acceptance criteria and tests linked | Not Started | High | 0 | Green
QUA-06 | Quality Engineering | 0-30 Foundation | [QE] Define test data management strategy including masking, synthetic data and reusable gold copy | IBM TDM Lead | Horizon Data Owner | 46223 | 46237 | 15 | QUA-03 | TDM strategy | Data privacy, reuse and refresh strategy approved | Not Started | High | 0 | Green
QUA-07 | Quality Engineering | 0-30 Foundation | [QE] Identify service virtualization/stub needs for APIs, batch, file feeds and external dependencies | IBM QE Architect | Horizon Integration Lead | 46228 | 46237 | 10 | QUA-04 | Service virtualization backlog | High-dependency flows prioritized | Not Started | High | 0 | Green
QUA-08 | Quality Engineering | 31-60 Production Ready | [QE] Stand up QE CoE operating model, standards, templates and metrics dashboard | IBM QE Lead | Horizon QA Lead | 46234 | 46248 | 15 | QUA-01;QUA-03 | QE CoE model | Common metrics and templates used by PODs | Not Started | High | 0 | Green
QUA-09 | Quality Engineering | 31-60 Production Ready | [QE] Rationalize existing regression suite and remove redundant / low-value tests | IBM QE Factory Lead | Horizon QA Lead | 46238 | 46257 | 20 | QUA-04 | Optimized regression pack | Regression pack reduced without coverage loss | Not Started | High | 0 | Green
QUA-10 | Quality Engineering | 31-60 Production Ready | [QE] Implement AI-assisted test case generation pilot from requirements/user stories | IBM QE Automation Lead | Horizon Product Owners | 46243 | 46262 | 20 | QUA-05 | AI test generation pilot | Req-to-test productivity baseline captured | Not Started | High | 0 | Green
QUA-11 | Quality Engineering | 31-60 Production Ready | [QE] Build automation framework enhancements for API, UI, component and batch regression | IBM QE Automation Lead | Horizon DevOps Lead | 46248 | 46267 | 20 | QUA-07;QUA-09 | Automation framework update | Reusable framework supports CI/CD integration | Not Started | High | 0 | Green
QUA-12 | Quality Engineering | 31-60 Production Ready | [QE] Create first automated smoke and regression packs for pilot product POD | IBM QE Automation Lead | Horizon QA Lead | 46258 | 46272 | 15 | QUA-10;QUA-11 | Pilot automated pack | Smoke tests executable in pipeline | Not Started | High | 0 | Green
QUA-13 | Quality Engineering | 61-90 Standardize & Integrate | [QE] Integrate automated tests into CI/CD gates for pilot cloud applications | IBM DevSecOps Lead | Horizon DevOps Lead | 46264 | 46283 | 20 | QUA-11;QUA-12 | CI/CD quality gates | Automated tests triggered on builds/deployments | Not Started | High | 0 | Green
QUA-14 | Quality Engineering | 61-90 Standardize & Integrate | [QE] Implement TDM self-service intake and data request tracker for priority domains | IBM TDM Lead | Horizon Data Owner | 46268 | 46292 | 25 | QUA-06 | TDM intake tracker | Data request aging and reuse visible | Not Started | High | 0 | Green
QUA-15 | Quality Engineering | 61-90 Standardize & Integrate | [QE] Pilot service virtualization for top dependency-constrained flows | IBM QE Architect | Horizon Integration Lead | 46273 | 46292 | 20 | QUA-07;QUA-11 | Virtualized service pilot | Dependency wait time reduced for pilot flows | Not Started | High | 0 | Green
QUA-16 | Quality Engineering | 61-90 Standardize & Integrate | [QE] Launch defect prevention analytics: root cause categories, escaped defects and re-open trends | IBM QE Lead | Horizon QA Lead | 46278 | 46292 | 15 | QUA-08;QUA-13 | Defect analytics dashboard | Defect leakage and repeat causes tracked | Not Started | High | 0 | Green
QUA-17 | Quality Engineering | 91-180 Scale & Optimize | [QE] Scale automation to additional product PODs based on business criticality | IBM QE Factory Lead | Horizon Product Owners | 46294 | 46323 | 30 | QUA-12;QUA-13 | Scaled automation backlog | Automation coverage improves monthly | Not Started | High | 0 | Green
QUA-18 | Quality Engineering | 91-180 Scale & Optimize | [QE] Deploy agentic QE workflow: requirements-to-test, test-to-BDD and BDD-to-automation | IBM QE Automation Lead | Horizon Tooling Lead | 46303 | 46332 | 30 | QUA-10;QUA-17 | Agentic QE workflow | Time-to-test reduction measured | Not Started | High | 0 | Green
QUA-19 | Quality Engineering | 91-180 Scale & Optimize | [QE] Expand non-functional testing model: performance, resilience, security and accessibility checkpoints | IBM QE Architect | Horizon NFR Owners | 46323 | 46357 | 35 | QUA-03;QUA-13 | NFR testing playbook | NFR entry/exit criteria embedded | Not Started | High | 0 | Green
QUA-20 | Quality Engineering | 91-180 Scale & Optimize | [QE] Establish continuous regression and release readiness scorecard | IBM QE Lead | Horizon Release Manager | 46333 | 46362 | 30 | QUA-16;QUA-17 | Release readiness scorecard | Quality delivery to UAT/Prod tracked | Not Started | High | 0 | Green
QUA-21 | Quality Engineering | 91-180 Scale & Optimize | [QE] Conduct 180-day QE maturity reassessment and finalize scale roadmap | IBM QE Lead | Horizon QA Lead | 46353 | 46382 | 30 | QUA-18;QUA-20 | QE scale roadmap | Maturity improvement and next-wave roadmap approved | Not Started | High | 0 | Green
AIO-01 | AIOps Implementation | 0-30 Foundation | Confirm AIOps scope, target architecture, ARB/security path and first 5 AWS-hosted applications | IBM AIOps Program Manager | Horizon ARB / Security | 46204 | 46208 | 5 |  | AIOps implementation charter | Scope and approval path agreed | Not Started | High | 0 | Green
AIO-02 | AIOps Implementation | 0-30 Foundation | Provision AIOps dev/test environments and connectivity pattern for Horizon ecosystem | IBM AIOps Architect | Horizon Infrastructure Lead | 46207 | 46216 | 10 | AIO-01 | AIOps environment ready | Environment provisioned; connectivity tested | Not Started | High | 0 | Green
AIO-03 | AIOps Implementation | 0-30 Foundation | Ingest historical ITSM ticket data and establish ticket taxonomy, resolution patterns and knowledge sources | IBM AIOps Data Lead | Horizon ITSM Lead | 46211 | 46222 | 12 | AIO-01 | Historical data ingestion | Ticket data loaded and normalized | Not Started | High | 0 | Green
AIO-04 | AIOps Implementation | 0-30 Foundation | Integrate ServiceNow/ClearQuest transition considerations and define ITSM workflow interfaces | IBM ITSM Integration Lead | Horizon ITSM Lead | 46215 | 46226 | 12 | AIO-01;AIO-03 | ITSM integration design | Workflow and data contracts agreed | Not Started | High | 0 | Green
AIO-05 | AIOps Implementation | 0-30 Foundation | Connect priority monitoring sources and logs for first cloud-app pilot set | IBM Observability Lead | Horizon Monitoring Lead | 46218 | 46232 | 15 | AIO-02 | Pilot observability integrations | Initial alerts/logs flowing | Not Started | High | 0 | Green
AIO-06 | AIOps Implementation | 0-30 Foundation | Configure default AIOps dashboards for operations, leadership and product teams | IBM AIOps Lead | Horizon Operations Lead | 46223 | 46232 | 10 | AIO-03;AIO-05 | Default dashboards | Operational visibility available | Not Started | High | 0 | Green
AIO-07 | AIOps Implementation | 0-30 Foundation | Train initial models for alert grouping, noise reduction and auto-triage | IBM AIOps Data Scientist | Horizon Operations SMEs | 46228 | 46242 | 15 | AIO-03;AIO-05 | Model training baseline | Initial auto-triage accuracy baseline | Not Started | High | 0 | Green
AIO-08 | AIOps Implementation | 31-60 Production Ready | Validate auto-triage for first 5 AWS-hosted applications with human-in-the-loop governance | IBM AIOps Lead | Horizon Operations Lead | 46234 | 46253 | 20 | AIO-05;AIO-07 | Auto-triage pilot | Pilot apps validated for triage recommendations | Not Started | High | 0 | Green
AIO-09 | AIOps Implementation | 31-60 Production Ready | Curate knowledge corpus from runbooks, SOPs, RCA and incident resolutions | IBM Knowledge Manager | Horizon SMEs | 46238 | 46257 | 20 | AIO-03;AIO-07 | Knowledge corpus | Runbooks and resolutions searchable by agents | Not Started | High | 0 | Green
AIO-10 | AIOps Implementation | 31-60 Production Ready | Define controlled auto-remediation candidate backlog and risk guardrails | IBM SRE Lead | Horizon Risk / Security | 46248 | 46262 | 15 | AIO-08;AIO-09 | Runbook automation backlog | Low-risk candidates approved | Not Started | High | 0 | Green
AIO-11 | AIOps Implementation | 61-90 Standardize & Integrate | Standardize log, event and alert normalization across cloud applications | IBM Observability Lead | Horizon Monitoring Lead | 46264 | 46283 | 20 | AIO-08;AIO-09 | Standardized ingestion rules | Consistent alert taxonomy across cloud apps | Not Started | High | 0 | Green
AIO-12 | AIOps Implementation | 61-90 Standardize & Integrate | Onboard remaining cloud applications and selected on-premise systems to AIOps ingestion | IBM AIOps Lead | Horizon App Owners | 46268 | 46292 | 25 | AIO-11 | Expanded AIOps onboarding | Coverage expanded beyond pilot apps | Not Started | High | 0 | Green
AIO-13 | AIOps Implementation | 61-90 Standardize & Integrate | Enable AI-assisted recommendations for high-volume incident categories | IBM AIOps Data Scientist | Horizon Operations SMEs | 46273 | 46292 | 20 | AIO-09;AIO-11 | Recommendation engine pilot | Recommendations available for priority incidents | Not Started | High | 0 | Green
AIO-14 | AIOps Implementation | 61-90 Standardize & Integrate | Pilot auto-healing for system-generated, low-risk incidents with audit trail | IBM SRE Lead | Horizon Security / Operations | 46278 | 46297 | 20 | AIO-10;AIO-13 | Auto-healing pilot | Remediation success/failures audited | Not Started | High | 0 | Green
AIO-15 | AIOps Implementation | 91-180 Scale & Optimize | Expand proactive alerting and predictive insights before business impact | IBM AIOps Lead | Horizon Operations Lead | 46294 | 46323 | 30 | AIO-12;AIO-13 | Predictive alerting capability | Incidents prevented or detected earlier | Not Started | High | 0 | Green
AIO-16 | AIOps Implementation | 91-180 Scale & Optimize | Integrate infrastructure logs and operational KPIs into single-pane AIOps view | IBM Observability Lead | Horizon Infrastructure Lead | 46303 | 46332 | 30 | AIO-12 | Infrastructure observability integration | Infra and app signals visible together | Not Started | High | 0 | Green
AIO-17 | AIOps Implementation | 91-180 Scale & Optimize | Scale auto-recommendations toward 50% of incoming incidents for cloud applications | IBM AIOps Data Scientist | Horizon Operations Lead | 46313 | 46347 | 35 | AIO-13;AIO-15 | Scaled recommendations | Recommendation coverage and acceptance tracked | Not Started | High | 0 | Green
AIO-18 | AIOps Implementation | 91-180 Scale & Optimize | Scale runbook automation across top repeatable incident and service request patterns | IBM SRE Lead | Horizon Operations Lead | 46328 | 46362 | 35 | AIO-14;AIO-17 | Runbook automation scale | Automation closures and MTTR impact measured | Not Started | High | 0 | Green
AIO-19 | AIOps Implementation | 91-180 Scale & Optimize | Operationalize AIOps governance: model feedback, guardrails, auditability and KPI review | IBM AIOps Program Manager | Horizon Risk / Compliance | 46348 | 46372 | 25 | AIO-14;AIO-18 | AIOps governance model | Human-in-loop and audit controls active | Not Started | High | 0 | Green
AIO-20 | AIOps Implementation | 91-180 Scale & Optimize | Complete 180-day AIOps value assessment and next-wave autonomous operations roadmap | IBM AIOps Program Manager | Horizon Executive Sponsor | 46363 | 46382 | 20 | AIO-18;AIO-19 | AIOps value assessment | MTTR/noise/productivity progress captured | Not Started | High | 0 | Green
CAR-01 | CareOps360 | 0-30 Foundation | Secure CareOps360 MVP scope, executive dashboard personas and success criteria | CareOps360 Product Owner | Horizon Transformation Sponsor | 46204 | 46208 | 5 |  | MVP scope and dashboard personas | MVP personas and dashboard objectives approved | Not Started | High | 0 | Green
CAR-02 | CareOps360 | 0-30 Foundation | Obtain ARB Light approval and define MVP deployment architecture | CareOps360 Architect | Horizon ARB / Security | 46206 | 46213 | 8 | CAR-01 | ARB Light approval package | MVP approval path clear | Not Started | High | 0 | Green
CAR-03 | CareOps360 | 0-30 Foundation | Deploy containerized CareOps360 to OCP/AWS dev environment | CareOps360 Engineering Lead | Horizon Platform Lead | 46208 | 46217 | 10 | CAR-02 | CareOps360 dev deployment | Application deployed in dev | Not Started | High | 0 | Green
CAR-04 | CareOps360 | 0-30 Foundation | Provision RDS Postgres schema and baseline data model for dashboards | CareOps360 Data Lead | Horizon Data Owner | 46211 | 46220 | 10 | CAR-02 | Data schema and model | Schema ready for MVP data loads | Not Started | High | 0 | Green
CAR-05 | CareOps360 | 0-30 Foundation | Manually load initial data for Executive Overview, Claims, Prior Auth and Providers views | CareOps360 Data Lead | Horizon Domain Owners | 46213 | 46227 | 15 | CAR-04 | Initial dashboard data loads | MVP views populated | Not Started | High | 0 | Green
CAR-06 | CareOps360 | 0-30 Foundation | Configure dashboard layouts, KPI definitions and role-based page access | CareOps360 Product Owner | Horizon Business Owners | 46218 | 46229 | 12 | CAR-01;CAR-05 | MVP dashboard configuration | Dashboard tiles and KPIs validated | Not Started | High | 0 | Green
CAR-07 | CareOps360 | 0-30 Foundation | Conduct MVP playback and prioritize production hardening backlog | CareOps360 Product Owner | Horizon Stakeholders | 46228 | 46237 | 10 | CAR-03;CAR-06 | MVP playback readout | Feedback converted to backlog | Not Started | High | 0 | Green
CAR-08 | CareOps360 | 31-60 Production Ready | Promote MVP through Horizon release process with SSO and RBAC configured | CareOps360 Engineering Lead | Horizon Security / Release | 46234 | 46248 | 15 | CAR-07 | Production-ready MVP | SSO/RBAC and release gates passed | Not Started | High | 0 | Green
CAR-09 | CareOps360 | 31-60 Production Ready | Design target-state near-real-time architecture with Kafka/MSK and data contracts | CareOps360 Architect | Horizon Data / Integration | 46238 | 46257 | 20 | CAR-04;CAR-07 | Target architecture | Data contracts and integration pattern approved | Not Started | High | 0 | Green
CAR-10 | CareOps360 | 31-60 Production Ready | Obtain ARB approval for target CareOps360 architecture | CareOps360 Architect | Horizon ARB / Security | 46248 | 46262 | 15 | CAR-09 | ARB approval | Target architecture approved | Not Started | High | 0 | Green
CAR-11 | CareOps360 | 31-60 Production Ready | Define CareOps360 operating model, support model and product ownership cadence | CareOps360 Product Owner | Horizon Product Owners | 46253 | 46262 | 10 | CAR-08 | CareOps360 operating model | Backlog and release cadence active | Not Started | High | 0 | Green
CAR-12 | CareOps360 | 61-90 Standardize & Integrate | Build ingestion platform in AWS using infrastructure-as-code, MSK and observability tools | CareOps360 Engineering Lead | Horizon Platform Lead | 46264 | 46283 | 20 | CAR-09;CAR-10 | Automated ingestion platform | IaC pipeline and MSK foundation built | Not Started | High | 0 | Green
CAR-13 | CareOps360 | 61-90 Standardize & Integrate | Automate top 4-6 sources including ServiceNow, APM and Databricks | CareOps360 Data Lead | Horizon Source Owners | 46268 | 46287 | 20 | CAR-12 | Automated source integrations | Priority integrations automated | Not Started | High | 0 | Green
CAR-14 | CareOps360 | 61-90 Standardize & Integrate | Enable previously-disabled dashboard tiles and validate data quality rules | CareOps360 Product Owner | Horizon Business Owners | 46278 | 46292 | 15 | CAR-13 | Expanded dashboard tiles | Tiles refreshed automatically with DQ rules | Not Started | High | 0 | Green
CAR-15 | CareOps360 | 61-90 Standardize & Integrate | Publish adoption plan, training assets and leadership consumption cadence | CareOps360 Change Lead | Horizon Transformation Office | 46288 | 46297 | 10 | CAR-14 | Adoption and training pack | Users onboarded; consumption cadence active | Not Started | High | 0 | Green
CAR-16 | CareOps360 | 91-180 Scale & Optimize | Migrate remaining sources including Contact Center, RPA and Provider Data Management | CareOps360 Data Lead | Horizon Source Owners | 46294 | 46323 | 30 | CAR-13;CAR-15 | Remaining source migration | Broader operational signal coverage | Not Started | High | 0 | Green
CAR-17 | CareOps360 | 91-180 Scale & Optimize | Activate AI Insights and Operations Copilot for trend explanation and next-best-action prompts | CareOps360 AI Lead | Horizon Operations Lead | 46303 | 46327 | 25 | CAR-14;CAR-16 | AI Insights / Copilot | AI narratives and recommendations visible | Not Started | High | 0 | Green
CAR-18 | CareOps360 | 91-180 Scale & Optimize | Implement write-back workflows to ServiceNow/Jira with guardrails and auditability | CareOps360 Engineering Lead | Horizon ITSM / Jira Owners | 46318 | 46347 | 30 | CAR-17 | Write-back workflows | Actions are traceable and controlled | Not Started | High | 0 | Green
CAR-19 | CareOps360 | 91-180 Scale & Optimize | Harden for scale with HA/DR, CI/CD maturity, resiliency testing and support runbooks | CareOps360 Architect | Horizon Platform Lead | 46333 | 46362 | 30 | CAR-18 | Scale hardening | HA/DR and CI/CD maturity validated | Not Started | High | 0 | Green
CAR-20 | CareOps360 | 91-180 Scale & Optimize | Complete 180-day CareOps360 value review and next capability roadmap | CareOps360 Product Owner | Horizon Executive Sponsor | 46363 | 46382 | 20 | CAR-17;CAR-19 | CareOps360 180-day roadmap | Adoption, value and next-wave capabilities approved | Not Started | High | 0 | Green
AGI-01 | Agile Product Model | 0-30 Foundation | Confirm agile/product transformation scope, leadership alignment and pilot selection criteria | IBM Product Transformation Lead | Horizon Executive Sponsor | 46204 | 46208 | 5 |  | Agile/product transformation charter | Pilot selection criteria agreed | Not Started | High | 0 | Green
AGI-02 | Agile Product Model | 0-30 Foundation | Assess current work intake, prioritization, funding, release and governance practices | IBM Agile Coach | Horizon PMO / Portfolio | 46208 | 46217 | 10 | AGI-01 | Current-state assessment | Pain points and change impacts documented | Not Started | High | 0 | Green
AGI-03 | Agile Product Model | 0-30 Foundation | Define product/value-stream taxonomy and map applications to candidate product domains | IBM Product Engineering Lead | Horizon Product Owners | 46211 | 46222 | 12 | AGI-01 | Domain/product map | Product domains and ownership draft | Not Started | High | 0 | Green
AGI-04 | Agile Product Model | 0-30 Foundation | Identify first-wave agile enhancement projects and pilot product stream | IBM Transformation Lead | Horizon Product Owners | 46215 | 46224 | 10 | AGI-02;AGI-03 | Pilot product stream selection | Pilot selected and leadership approved | Not Started | High | 0 | Green
AGI-05 | Agile Product Model | 0-30 Foundation | Define product roles, RACI, POD composition, scrum ceremonies and decision rights | IBM Agile Coach | Horizon Product Owners | 46218 | 46232 | 15 | AGI-04 | POD operating model | Roles and decision rights clear | Not Started | High | 0 | Green
AGI-06 | Agile Product Model | 0-30 Foundation | Create pilot backlog foundation with epics, features, stories, acceptance criteria and KPIs | IBM Product Owner Coach | Horizon Product Owner | 46223 | 46234 | 12 | AGI-04;AGI-05 | Pilot backlog | Backlog ready for sprint planning | Not Started | High | 0 | Green
AGI-07 | Agile Product Model | 0-30 Foundation | Train pilot PODs on agile ways of working, product mindset and outcome-based metrics | IBM Agile Coach | Horizon POD Members | 46228 | 46237 | 10 | AGI-05;AGI-06 | Training completion | Pilot team trained and ready | Not Started | High | 0 | Green
AGI-08 | Agile Product Model | 31-60 Production Ready | Launch sprint 0 for pilot POD including tooling, definition of ready/done and release plan | IBM Scrum Master | Horizon Product Owner | 46234 | 46243 | 10 | AGI-06;AGI-07 | Sprint 0 readiness | Team ready for sprint execution | Not Started | High | 0 | Green
AGI-09 | Agile Product Model | 31-60 Production Ready | Execute pilot sprint 1-2 with coaching, demos, retrospectives and dependency management | IBM Scrum Master | Horizon Product Owner | 46243 | 46262 | 20 | AGI-08 | Pilot sprint outcomes | Velocity, impediments and demo feedback captured | Not Started | High | 0 | Green
AGI-10 | Agile Product Model | 31-60 Production Ready | Establish product metrics dashboard: velocity, predictability, backlog health, value and quality | IBM Transformation Office | Horizon PMO | 46253 | 46262 | 10 | AGI-08;AGI-09 | Product metrics dashboard | Metrics visible for pilot POD | Not Started | High | 0 | Green
AGI-11 | Agile Product Model | 61-90 Standardize & Integrate | Standardize intake and prioritization workflow across pilot products and AMS requests | IBM Product Transformation Lead | Horizon Portfolio Lead | 46264 | 46283 | 20 | AGI-09;AGI-10 | Standard intake workflow | Demand routed and prioritized by value | Not Started | High | 0 | Green
AGI-12 | Agile Product Model | 61-90 Standardize & Integrate | Scale agile ceremonies and product backlog model to next-wave PODs | IBM Agile Coach | Horizon Product Owners | 46268 | 46292 | 25 | AGI-09;AGI-11 | Next-wave POD setup | Additional PODs operating with common cadence | Not Started | High | 0 | Green
AGI-13 | Agile Product Model | 61-90 Standardize & Integrate | Integrate DevSecOps 2.0 practices and quality gates into pilot / cloud app PODs | IBM DevSecOps Lead | Horizon DevOps Lead | 46278 | 46292 | 15 | AGI-08;AGI-12 | DevSecOps adoption plan | Pipeline gates and security checks embedded | Not Started | High | 0 | Green
AGI-14 | Agile Product Model | 61-90 Standardize & Integrate | Conduct 90-day product model health review and refine operating model | IBM Product Transformation Lead | Horizon Executive Sponsor | 46293 | 46312 | 20 | AGI-10;AGI-12;AGI-13 | 90-day health review | Model refinements approved | Not Started | High | 0 | Green
AGI-15 | Agile Product Model | 91-180 Scale & Optimize | Expand product/value-stream governance into monthly portfolio and quarterly value reviews | IBM Transformation Office | Horizon PMO | 46294 | 46323 | 30 | AGI-14 | Product governance cadence | Roadmap, value and capacity reviews live | Not Started | High | 0 | Green
AGI-16 | Agile Product Model | 91-180 Scale & Optimize | Build product roadmaps for priority domains covering BAU, tech debt and transformation items | IBM Product Owners / Coaches | Horizon Product Owners | 46303 | 46337 | 35 | AGI-11;AGI-15 | Product roadmaps | Domain roadmaps aligned to business outcomes | Not Started | High | 0 | Green
AGI-17 | Agile Product Model | 91-180 Scale & Optimize | Embed innovation sprint cadence and market/payer trend backlog intake | IBM Transformation Lead | Horizon Product Owners | 46318 | 46347 | 30 | AGI-15;AGI-16 | Innovation sprint model | Quarterly innovation intake live | Not Started | High | 0 | Green
AGI-18 | Agile Product Model | 91-180 Scale & Optimize | Optimize POD capacity model, talent rotation and skill evolution for AI/cloud/data needs | IBM Delivery Lead | Horizon Resource Owners | 46333 | 46357 | 25 | AGI-12;AGI-16 | Capacity and skill roadmap | Talent rotation plan tied to roadmap | Not Started | High | 0 | Green
AGI-19 | Agile Product Model | 91-180 Scale & Optimize | Complete 180-day agile/product maturity assessment and scale roadmap | IBM Product Transformation Lead | Horizon Executive Sponsor | 46353 | 46382 | 30 | AGI-16;AGI-18 | Agile/product scale roadmap | Maturity delta and scale roadmap approved | Not Started | High | 0 | Green
Formulas:
RAG = IF([Status]="Completed","Green",IF(TODAY()>[End Date],"Red",IF(AND(TODAY()+14>[End Date],O2<0.75),"Amber","Green")))

## Overall Transition
ID | Workstream | Phase | Task / Activity | IBM Owner | Horizon Owner | Start Date | End Date | Duration Days | Dependencies | Deliverable / Milestone | Success Metric | Status | Priority | % Complete | RAG | Notes
OVE-01 | Overall Transition | 0-30 Foundation | Confirm transition charter, scope, governance cadence and 180-day success criteria | IBM Transformation Lead | Horizon Executive Sponsor | 46204 | 46206 | 3 |  | Signed transition charter | Steering cadence active; 180-day KPIs approved | Not Started | High | 0 | Green
OVE-02 | Overall Transition | 0-30 Foundation | Establish integrated transition command center and daily/weekly operating rhythm | IBM Delivery Lead | Horizon PMO | 46204 | 46208 | 5 | TR-01 | Transition command center | Daily standups, weekly operating review, escalation path live | Not Started | High | 0 | Green
OVE-03 | Overall Transition | 0-30 Foundation | Validate in-scope applications, services, SLAs, owners and incumbent knowledge repositories | IBM Transition Manager | Horizon App Owners | 46207 | 46213 | 7 | TR-01 | Validated inventory and SLA baseline | 100% critical services mapped | Not Started | High | 0 | Green
OVE-04 | Overall Transition | 0-30 Foundation | Complete access, environment, tooling and onboarding plan for IBM transition resources | IBM Delivery Lead | Horizon Security / ITSM | 46207 | 46216 | 10 | TR-01 | Access tracker and onboarding plan | Access SLA agreed; blockers visible | Not Started | High | 0 | Green
OVE-05 | Overall Transition | 0-30 Foundation | Execute knowledge transfer wave 1 for critical applications and operations processes | IBM App Leads | Horizon SMEs | 46211 | 46220 | 10 | TR-03;TR-04 | KT wave 1 artifacts | Critical apps have runbooks, support matrix and SME sign-off | Not Started | High | 0 | Green
OVE-06 | Overall Transition | 0-30 Foundation | Baseline current incident, request, change, defect and deployment metrics | IBM Service Delivery Manager | Horizon ITSM Lead | 46215 | 46226 | 12 | TR-03 | Operational baseline dashboard | MTTR, ticket volume, backlog aging and SLA baseline captured | Not Started | High | 0 | Green
OVE-07 | Overall Transition | 0-30 Foundation | Map AMS towers to initial product/value-stream POD structure | IBM Product Engineering Lead | Horizon Product Owners | 46218 | 46227 | 10 | TR-03 | Initial POD alignment map | Applications mapped to domains/value streams | Not Started | High | 0 | Green
OVE-08 | Overall Transition | 0-30 Foundation | Finalize interim run/support model and hypercare approach for first 60 days | IBM Delivery Lead | Horizon Operations Lead | 46225 | 46234 | 10 | TR-02;TR-05 | Run support model | No service disruption; escalation path tested | Not Started | High | 0 | Green
OVE-09 | Overall Transition | 31-60 Production Ready | Stabilize delivery governance, integrated risk log, dependency log and executive reporting | IBM Transformation Office | Horizon PMO | 46234 | 46248 | 15 | TR-02;TR-06 | Governance pack | Weekly reporting with risks, dependencies and KPIs | Not Started | High | 0 | Green
OVE-10 | Overall Transition | 31-60 Production Ready | Complete knowledge transfer wave 2 for business-critical and medium-critical applications | IBM App Leads | Horizon SMEs | 46234 | 46253 | 20 | TR-05 | KT wave 2 artifacts | >85% KT completion; gaps documented | Not Started | High | 0 | Green
OVE-11 | Overall Transition | 31-60 Production Ready | Transition service delivery accountability to IBM POD/service leads with shadow-to-reverse-shadow plan | IBM Delivery Lead | Horizon Operations Lead | 46243 | 46257 | 15 | TR-08;TR-10 | Service transition cutover checklist | POD leads own daily execution | Not Started | High | 0 | Green
OVE-12 | Overall Transition | 31-60 Production Ready | Implement SLA/CSL reporting pack aligned to business KPIs and operational metrics | IBM Service Delivery Manager | Horizon ITSM Lead | 46248 | 46262 | 15 | TR-06;TR-09 | SLA/CSL dashboard | Business KPIs and critical service levels visible monthly | Not Started | High | 0 | Green
OVE-13 | Overall Transition | 61-90 Standardize & Integrate | Optimize support model based on 60-day learnings and adjust staffing by product demand | IBM Delivery Lead | Horizon Product Owners | 46264 | 46283 | 20 | TR-11;TR-12 | Optimized support model | Backlog and incident queues balanced by domain | Not Started | High | 0 | Green
OVE-14 | Overall Transition | 61-90 Standardize & Integrate | Launch transformation backlog intake for tech debt, ticket reduction and strategic initiatives | IBM Transformation Lead | Horizon Portfolio Lead | 46264 | 46288 | 25 | TR-09 | Transformation backlog | Initiatives scored by value, risk and feasibility | Not Started | High | 0 | Green
OVE-15 | Overall Transition | 61-90 Standardize & Integrate | Run first value realization review and confirm reinvestment / modernization candidates | IBM Transformation Lead | Horizon Executive Sponsor | 46278 | 46292 | 15 | TR-14 | Value review readout | Savings and value opportunities quantified | Not Started | High | 0 | Green
OVE-16 | Overall Transition | 91-180 Scale & Optimize | Scale transition governance into product-centric monthly/quarterly operating model | IBM Transformation Office | Horizon PMO | 46294 | 46323 | 30 | TR-13;TR-15 | Quarterly operating model | Product roadmap, KPI, financial and value governance running | Not Started | High | 0 | Green
OVE-17 | Overall Transition | 91-180 Scale & Optimize | Implement continuous improvement loop for incidents, RCA, automation and knowledge updates | IBM SRE / Ops Lead | Horizon Operations Lead | 46303 | 46347 | 45 | TR-13 | Continuous improvement backlog | Repeat incidents trend down; RCA actions tracked | Not Started | High | 0 | Green
OVE-18 | Overall Transition | 91-180 Scale & Optimize | Finalize Year-1 transformation roadmap refresh using 180-day operating data | IBM Transformation Lead | Horizon Executive Sponsor | 46323 | 46367 | 45 | TR-15;TR-17 | Year-1 roadmap refresh | Funded roadmap with near-term priorities | Not Started | High | 0 | Green
OVE-19 | Overall Transition | 91-180 Scale & Optimize | Execute 180-day transition health assessment and transition-to-steady-state acceptance | IBM Delivery Lead | Horizon Executive Sponsor | 46353 | 46382 | 30 | TR-16;TR-18 | 180-day acceptance report | Steady-state acceptance and remaining actions signed off | Not Started | High | 0 | Green
Formulas:
RAG = IF([Status]="Completed","Green",IF(TODAY()>[End Date],"Red",IF(AND(TODAY()+14>[End Date],O2<0.75),"Amber","Green")))

## Quality Engineering
ID | Workstream | Phase | Task / Activity | IBM Owner | Horizon Owner | Start Date | End Date | Duration Days | Dependencies | Deliverable / Milestone | Success Metric | Status | Priority | % Complete | RAG | Notes
QUA-01 | Quality Engineering | 0-30 Foundation | [QE] Mobilize QE transition team, clarify testing scope and confirm QE governance | IBM QE Lead | Horizon QA Lead | 46204 | 46208 | 5 |  | QE mobilization plan | QE governance and owners confirmed | Not Started | High | 0 | Green
QUA-02 | Quality Engineering | 0-30 Foundation | [QE] Assess current test assets, automation coverage, defect leakage and regression cycle health | IBM QE Architect | Horizon QA Lead | 46207 | 46214 | 8 | QUA-01 | QE maturity assessment | Automation baseline, test pack gaps and defect trends documented | Not Started | High | 0 | Green
QUA-03 | Quality Engineering | 0-30 Foundation | [QE] Define end-to-end QE strategy: shift-left, BDD/TDD, SIT, UAT support and non-functional testing | IBM QE Lead | Horizon QA Lead | 46211 | 46220 | 10 | QUA-02 | QE strategy and playbook | Standardized test lifecycle agreed | Not Started | High | 0 | Green
QUA-04 | Quality Engineering | 0-30 Foundation | [QE] Inventory critical business flows and identify regression pack rationalization opportunities | IBM QE Analyst | Horizon Business SMEs | 46215 | 46226 | 12 | QUA-02 | Critical flow catalog | Top flows prioritized by business risk | Not Started | High | 0 | Green
QUA-05 | Quality Engineering | 0-30 Foundation | [QE] Establish requirement-to-test traceability model in Jira/GitHub/toolchain | IBM QE Architect | Horizon Tooling Lead | 46219 | 46233 | 15 | QUA-03 | Traceability model | Stories, acceptance criteria and tests linked | Not Started | High | 0 | Green
QUA-06 | Quality Engineering | 0-30 Foundation | [QE] Define test data management strategy including masking, synthetic data and reusable gold copy | IBM TDM Lead | Horizon Data Owner | 46223 | 46237 | 15 | QUA-03 | TDM strategy | Data privacy, reuse and refresh strategy approved | Not Started | High | 0 | Green
QUA-07 | Quality Engineering | 0-30 Foundation | [QE] Identify service virtualization/stub needs for APIs, batch, file feeds and external dependencies | IBM QE Architect | Horizon Integration Lead | 46228 | 46237 | 10 | QUA-04 | Service virtualization backlog | High-dependency flows prioritized | Not Started | High | 0 | Green
QUA-08 | Quality Engineering | 31-60 Production Ready | [QE] Stand up QE CoE operating model, standards, templates and metrics dashboard | IBM QE Lead | Horizon QA Lead | 46234 | 46248 | 15 | QUA-01;QUA-03 | QE CoE model | Common metrics and templates used by PODs | Not Started | High | 0 | Green
QUA-09 | Quality Engineering | 31-60 Production Ready | [QE] Rationalize existing regression suite and remove redundant / low-value tests | IBM QE Factory Lead | Horizon QA Lead | 46238 | 46257 | 20 | QUA-04 | Optimized regression pack | Regression pack reduced without coverage loss | Not Started | High | 0 | Green
QUA-10 | Quality Engineering | 31-60 Production Ready | [QE] Implement AI-assisted test case generation pilot from requirements/user stories | IBM QE Automation Lead | Horizon Product Owners | 46243 | 46262 | 20 | QUA-05 | AI test generation pilot | Req-to-test productivity baseline captured | Not Started | High | 0 | Green
QUA-11 | Quality Engineering | 31-60 Production Ready | [QE] Build automation framework enhancements for API, UI, component and batch regression | IBM QE Automation Lead | Horizon DevOps Lead | 46248 | 46267 | 20 | QUA-07;QUA-09 | Automation framework update | Reusable framework supports CI/CD integration | Not Started | High | 0 | Green
QUA-12 | Quality Engineering | 31-60 Production Ready | [QE] Create first automated smoke and regression packs for pilot product POD | IBM QE Automation Lead | Horizon QA Lead | 46258 | 46272 | 15 | QUA-10;QUA-11 | Pilot automated pack | Smoke tests executable in pipeline | Not Started | High | 0 | Green
QUA-13 | Quality Engineering | 61-90 Standardize & Integrate | [QE] Integrate automated tests into CI/CD gates for pilot cloud applications | IBM DevSecOps Lead | Horizon DevOps Lead | 46264 | 46283 | 20 | QUA-11;QUA-12 | CI/CD quality gates | Automated tests triggered on builds/deployments | Not Started | High | 0 | Green
QUA-14 | Quality Engineering | 61-90 Standardize & Integrate | [QE] Implement TDM self-service intake and data request tracker for priority domains | IBM TDM Lead | Horizon Data Owner | 46268 | 46292 | 25 | QUA-06 | TDM intake tracker | Data request aging and reuse visible | Not Started | High | 0 | Green
QUA-15 | Quality Engineering | 61-90 Standardize & Integrate | [QE] Pilot service virtualization for top dependency-constrained flows | IBM QE Architect | Horizon Integration Lead | 46273 | 46292 | 20 | QUA-07;QUA-11 | Virtualized service pilot | Dependency wait time reduced for pilot flows | Not Started | High | 0 | Green
QUA-16 | Quality Engineering | 61-90 Standardize & Integrate | [QE] Launch defect prevention analytics: root cause categories, escaped defects and re-open trends | IBM QE Lead | Horizon QA Lead | 46278 | 46292 | 15 | QUA-08;QUA-13 | Defect analytics dashboard | Defect leakage and repeat causes tracked | Not Started | High | 0 | Green
QUA-17 | Quality Engineering | 91-180 Scale & Optimize | [QE] Scale automation to additional product PODs based on business criticality | IBM QE Factory Lead | Horizon Product Owners | 46294 | 46323 | 30 | QUA-12;QUA-13 | Scaled automation backlog | Automation coverage improves monthly | Not Started | High | 0 | Green
QUA-18 | Quality Engineering | 91-180 Scale & Optimize | [QE] Deploy agentic QE workflow: requirements-to-test, test-to-BDD and BDD-to-automation | IBM QE Automation Lead | Horizon Tooling Lead | 46303 | 46332 | 30 | QUA-10;QUA-17 | Agentic QE workflow | Time-to-test reduction measured | Not Started | High | 0 | Green
QUA-19 | Quality Engineering | 91-180 Scale & Optimize | [QE] Expand non-functional testing model: performance, resilience, security and accessibility checkpoints | IBM QE Architect | Horizon NFR Owners | 46323 | 46357 | 35 | QUA-03;QUA-13 | NFR testing playbook | NFR entry/exit criteria embedded | Not Started | High | 0 | Green
QUA-20 | Quality Engineering | 91-180 Scale & Optimize | [QE] Establish continuous regression and release readiness scorecard | IBM QE Lead | Horizon Release Manager | 46333 | 46362 | 30 | QUA-16;QUA-17 | Release readiness scorecard | Quality delivery to UAT/Prod tracked | Not Started | High | 0 | Green
QUA-21 | Quality Engineering | 91-180 Scale & Optimize | [QE] Conduct 180-day QE maturity reassessment and finalize scale roadmap | IBM QE Lead | Horizon QA Lead | 46353 | 46382 | 30 | QUA-18;QUA-20 | QE scale roadmap | Maturity improvement and next-wave roadmap approved | Not Started | High | 0 | Green
Formulas:
RAG = IF([Status]="Completed","Green",IF(TODAY()>[End Date],"Red",IF(AND(TODAY()+14>[End Date],O2<0.75),"Amber","Green")))

## AIOps Implementation
ID | Workstream | Phase | Task / Activity | IBM Owner | Horizon Owner | Start Date | End Date | Duration Days | Dependencies | Deliverable / Milestone | Success Metric | Status | Priority | % Complete | RAG | Notes
AIO-01 | AIOps Implementation | 0-30 Foundation | Confirm AIOps scope, target architecture, ARB/security path and first 5 AWS-hosted applications | IBM AIOps Program Manager | Horizon ARB / Security | 46204 | 46208 | 5 |  | AIOps implementation charter | Scope and approval path agreed | Not Started | High | 0 | Green
AIO-02 | AIOps Implementation | 0-30 Foundation | Provision AIOps dev/test environments and connectivity pattern for Horizon ecosystem | IBM AIOps Architect | Horizon Infrastructure Lead | 46207 | 46216 | 10 | AIO-01 | AIOps environment ready | Environment provisioned; connectivity tested | Not Started | High | 0 | Green
AIO-03 | AIOps Implementation | 0-30 Foundation | Ingest historical ITSM ticket data and establish ticket taxonomy, resolution patterns and knowledge sources | IBM AIOps Data Lead | Horizon ITSM Lead | 46211 | 46222 | 12 | AIO-01 | Historical data ingestion | Ticket data loaded and normalized | Not Started | High | 0 | Green
AIO-04 | AIOps Implementation | 0-30 Foundation | Integrate ServiceNow/ClearQuest transition considerations and define ITSM workflow interfaces | IBM ITSM Integration Lead | Horizon ITSM Lead | 46215 | 46226 | 12 | AIO-01;AIO-03 | ITSM integration design | Workflow and data contracts agreed | Not Started | High | 0 | Green
AIO-05 | AIOps Implementation | 0-30 Foundation | Connect priority monitoring sources and logs for first cloud-app pilot set | IBM Observability Lead | Horizon Monitoring Lead | 46218 | 46232 | 15 | AIO-02 | Pilot observability integrations | Initial alerts/logs flowing | Not Started | High | 0 | Green
AIO-06 | AIOps Implementation | 0-30 Foundation | Configure default AIOps dashboards for operations, leadership and product teams | IBM AIOps Lead | Horizon Operations Lead | 46223 | 46232 | 10 | AIO-03;AIO-05 | Default dashboards | Operational visibility available | Not Started | High | 0 | Green
AIO-07 | AIOps Implementation | 0-30 Foundation | Train initial models for alert grouping, noise reduction and auto-triage | IBM AIOps Data Scientist | Horizon Operations SMEs | 46228 | 46242 | 15 | AIO-03;AIO-05 | Model training baseline | Initial auto-triage accuracy baseline | Not Started | High | 0 | Green
AIO-08 | AIOps Implementation | 31-60 Production Ready | Validate auto-triage for first 5 AWS-hosted applications with human-in-the-loop governance | IBM AIOps Lead | Horizon Operations Lead | 46234 | 46253 | 20 | AIO-05;AIO-07 | Auto-triage pilot | Pilot apps validated for triage recommendations | Not Started | High | 0 | Green
AIO-09 | AIOps Implementation | 31-60 Production Ready | Curate knowledge corpus from runbooks, SOPs, RCA and incident resolutions | IBM Knowledge Manager | Horizon SMEs | 46238 | 46257 | 20 | AIO-03;AIO-07 | Knowledge corpus | Runbooks and resolutions searchable by agents | Not Started | High | 0 | Green
AIO-10 | AIOps Implementation | 31-60 Production Ready | Define controlled auto-remediation candidate backlog and risk guardrails | IBM SRE Lead | Horizon Risk / Security | 46248 | 46262 | 15 | AIO-08;AIO-09 | Runbook automation backlog | Low-risk candidates approved | Not Started | High | 0 | Green
AIO-11 | AIOps Implementation | 61-90 Standardize & Integrate | Standardize log, event and alert normalization across cloud applications | IBM Observability Lead | Horizon Monitoring Lead | 46264 | 46283 | 20 | AIO-08;AIO-09 | Standardized ingestion rules | Consistent alert taxonomy across cloud apps | Not Started | High | 0 | Green
AIO-12 | AIOps Implementation | 61-90 Standardize & Integrate | Onboard remaining cloud applications and selected on-premise systems to AIOps ingestion | IBM AIOps Lead | Horizon App Owners | 46268 | 46292 | 25 | AIO-11 | Expanded AIOps onboarding | Coverage expanded beyond pilot apps | Not Started | High | 0 | Green
AIO-13 | AIOps Implementation | 61-90 Standardize & Integrate | Enable AI-assisted recommendations for high-volume incident categories | IBM AIOps Data Scientist | Horizon Operations SMEs | 46273 | 46292 | 20 | AIO-09;AIO-11 | Recommendation engine pilot | Recommendations available for priority incidents | Not Started | High | 0 | Green
AIO-14 | AIOps Implementation | 61-90 Standardize & Integrate | Pilot auto-healing for system-generated, low-risk incidents with audit trail | IBM SRE Lead | Horizon Security / Operations | 46278 | 46297 | 20 | AIO-10;AIO-13 | Auto-healing pilot | Remediation success/failures audited | Not Started | High | 0 | Green
AIO-15 | AIOps Implementation | 91-180 Scale & Optimize | Expand proactive alerting and predictive insights before business impact | IBM AIOps Lead | Horizon Operations Lead | 46294 | 46323 | 30 | AIO-12;AIO-13 | Predictive alerting capability | Incidents prevented or detected earlier | Not Started | High | 0 | Green
AIO-16 | AIOps Implementation | 91-180 Scale & Optimize | Integrate infrastructure logs and operational KPIs into single-pane AIOps view | IBM Observability Lead | Horizon Infrastructure Lead | 46303 | 46332 | 30 | AIO-12 | Infrastructure observability integration | Infra and app signals visible together | Not Started | High | 0 | Green
AIO-17 | AIOps Implementation | 91-180 Scale & Optimize | Scale auto-recommendations toward 50% of incoming incidents for cloud applications | IBM AIOps Data Scientist | Horizon Operations Lead | 46313 | 46347 | 35 | AIO-13;AIO-15 | Scaled recommendations | Recommendation coverage and acceptance tracked | Not Started | High | 0 | Green
AIO-18 | AIOps Implementation | 91-180 Scale & Optimize | Scale runbook automation across top repeatable incident and service request patterns | IBM SRE Lead | Horizon Operations Lead | 46328 | 46362 | 35 | AIO-14;AIO-17 | Runbook automation scale | Automation closures and MTTR impact measured | Not Started | High | 0 | Green
AIO-19 | AIOps Implementation | 91-180 Scale & Optimize | Operationalize AIOps governance: model feedback, guardrails, auditability and KPI review | IBM AIOps Program Manager | Horizon Risk / Compliance | 46348 | 46372 | 25 | AIO-14;AIO-18 | AIOps governance model | Human-in-loop and audit controls active | Not Started | High | 0 | Green
AIO-20 | AIOps Implementation | 91-180 Scale & Optimize | Complete 180-day AIOps value assessment and next-wave autonomous operations roadmap | IBM AIOps Program Manager | Horizon Executive Sponsor | 46363 | 46382 | 20 | AIO-18;AIO-19 | AIOps value assessment | MTTR/noise/productivity progress captured | Not Started | High | 0 | Green
Formulas:
RAG = IF([Status]="Completed","Green",IF(TODAY()>[End Date],"Red",IF(AND(TODAY()+14>[End Date],O2<0.75),"Amber","Green")))

## CareOps360
ID | Workstream | Phase | Task / Activity | IBM Owner | Horizon Owner | Start Date | End Date | Duration Days | Dependencies | Deliverable / Milestone | Success Metric | Status | Priority | % Complete | RAG | Notes
CAR-01 | CareOps360 | 0-30 Foundation | Secure CareOps360 MVP scope, executive dashboard personas and success criteria | CareOps360 Product Owner | Horizon Transformation Sponsor | 46204 | 46208 | 5 |  | MVP scope and dashboard personas | MVP personas and dashboard objectives approved | Not Started | High | 0 | Green
CAR-02 | CareOps360 | 0-30 Foundation | Obtain ARB Light approval and define MVP deployment architecture | CareOps360 Architect | Horizon ARB / Security | 46206 | 46213 | 8 | CAR-01 | ARB Light approval package | MVP approval path clear | Not Started | High | 0 | Green
CAR-03 | CareOps360 | 0-30 Foundation | Deploy containerized CareOps360 to OCP/AWS dev environment | CareOps360 Engineering Lead | Horizon Platform Lead | 46208 | 46217 | 10 | CAR-02 | CareOps360 dev deployment | Application deployed in dev | Not Started | High | 0 | Green
CAR-04 | CareOps360 | 0-30 Foundation | Provision RDS Postgres schema and baseline data model for dashboards | CareOps360 Data Lead | Horizon Data Owner | 46211 | 46220 | 10 | CAR-02 | Data schema and model | Schema ready for MVP data loads | Not Started | High | 0 | Green
CAR-05 | CareOps360 | 0-30 Foundation | Manually load initial data for Executive Overview, Claims, Prior Auth and Providers views | CareOps360 Data Lead | Horizon Domain Owners | 46213 | 46227 | 15 | CAR-04 | Initial dashboard data loads | MVP views populated | Not Started | High | 0 | Green
CAR-06 | CareOps360 | 0-30 Foundation | Configure dashboard layouts, KPI definitions and role-based page access | CareOps360 Product Owner | Horizon Business Owners | 46218 | 46229 | 12 | CAR-01;CAR-05 | MVP dashboard configuration | Dashboard tiles and KPIs validated | Not Started | High | 0 | Green
CAR-07 | CareOps360 | 0-30 Foundation | Conduct MVP playback and prioritize production hardening backlog | CareOps360 Product Owner | Horizon Stakeholders | 46228 | 46237 | 10 | CAR-03;CAR-06 | MVP playback readout | Feedback converted to backlog | Not Started | High | 0 | Green
CAR-08 | CareOps360 | 31-60 Production Ready | Promote MVP through Horizon release process with SSO and RBAC configured | CareOps360 Engineering Lead | Horizon Security / Release | 46234 | 46248 | 15 | CAR-07 | Production-ready MVP | SSO/RBAC and release gates passed | Not Started | High | 0 | Green
CAR-09 | CareOps360 | 31-60 Production Ready | Design target-state near-real-time architecture with Kafka/MSK and data contracts | CareOps360 Architect | Horizon Data / Integration | 46238 | 46257 | 20 | CAR-04;CAR-07 | Target architecture | Data contracts and integration pattern approved | Not Started | High | 0 | Green
CAR-10 | CareOps360 | 31-60 Production Ready | Obtain ARB approval for target CareOps360 architecture | CareOps360 Architect | Horizon ARB / Security | 46248 | 46262 | 15 | CAR-09 | ARB approval | Target architecture approved | Not Started | High | 0 | Green
CAR-11 | CareOps360 | 31-60 Production Ready | Define CareOps360 operating model, support model and product ownership cadence | CareOps360 Product Owner | Horizon Product Owners | 46253 | 46262 | 10 | CAR-08 | CareOps360 operating model | Backlog and release cadence active | Not Started | High | 0 | Green
CAR-12 | CareOps360 | 61-90 Standardize & Integrate | Build ingestion platform in AWS using infrastructure-as-code, MSK and observability tools | CareOps360 Engineering Lead | Horizon Platform Lead | 46264 | 46283 | 20 | CAR-09;CAR-10 | Automated ingestion platform | IaC pipeline and MSK foundation built | Not Started | High | 0 | Green
CAR-13 | CareOps360 | 61-90 Standardize & Integrate | Automate top 4-6 sources including ServiceNow, APM and Databricks | CareOps360 Data Lead | Horizon Source Owners | 46268 | 46287 | 20 | CAR-12 | Automated source integrations | Priority integrations automated | Not Started | High | 0 | Green
CAR-14 | CareOps360 | 61-90 Standardize & Integrate | Enable previously-disabled dashboard tiles and validate data quality rules | CareOps360 Product Owner | Horizon Business Owners | 46278 | 46292 | 15 | CAR-13 | Expanded dashboard tiles | Tiles refreshed automatically with DQ rules | Not Started | High | 0 | Green
CAR-15 | CareOps360 | 61-90 Standardize & Integrate | Publish adoption plan, training assets and leadership consumption cadence | CareOps360 Change Lead | Horizon Transformation Office | 46288 | 46297 | 10 | CAR-14 | Adoption and training pack | Users onboarded; consumption cadence active | Not Started | High | 0 | Green
CAR-16 | CareOps360 | 91-180 Scale & Optimize | Migrate remaining sources including Contact Center, RPA and Provider Data Management | CareOps360 Data Lead | Horizon Source Owners | 46294 | 46323 | 30 | CAR-13;CAR-15 | Remaining source migration | Broader operational signal coverage | Not Started | High | 0 | Green
CAR-17 | CareOps360 | 91-180 Scale & Optimize | Activate AI Insights and Operations Copilot for trend explanation and next-best-action prompts | CareOps360 AI Lead | Horizon Operations Lead | 46303 | 46327 | 25 | CAR-14;CAR-16 | AI Insights / Copilot | AI narratives and recommendations visible | Not Started | High | 0 | Green
CAR-18 | CareOps360 | 91-180 Scale & Optimize | Implement write-back workflows to ServiceNow/Jira with guardrails and auditability | CareOps360 Engineering Lead | Horizon ITSM / Jira Owners | 46318 | 46347 | 30 | CAR-17 | Write-back workflows | Actions are traceable and controlled | Not Started | High | 0 | Green
CAR-19 | CareOps360 | 91-180 Scale & Optimize | Harden for scale with HA/DR, CI/CD maturity, resiliency testing and support runbooks | CareOps360 Architect | Horizon Platform Lead | 46333 | 46362 | 30 | CAR-18 | Scale hardening | HA/DR and CI/CD maturity validated | Not Started | High | 0 | Green
CAR-20 | CareOps360 | 91-180 Scale & Optimize | Complete 180-day CareOps360 value review and next capability roadmap | CareOps360 Product Owner | Horizon Executive Sponsor | 46363 | 46382 | 20 | CAR-17;CAR-19 | CareOps360 180-day roadmap | Adoption, value and next-wave capabilities approved | Not Started | High | 0 | Green
Formulas:
RAG = IF([Status]="Completed","Green",IF(TODAY()>[End Date],"Red",IF(AND(TODAY()+14>[End Date],O2<0.75),"Amber","Green")))

## Agile Product Model
ID | Workstream | Phase | Task / Activity | IBM Owner | Horizon Owner | Start Date | End Date | Duration Days | Dependencies | Deliverable / Milestone | Success Metric | Status | Priority | % Complete | RAG | Notes
AGI-01 | Agile Product Model | 0-30 Foundation | Confirm agile/product transformation scope, leadership alignment and pilot selection criteria | IBM Product Transformation Lead | Horizon Executive Sponsor | 46204 | 46208 | 5 |  | Agile/product transformation charter | Pilot selection criteria agreed | Not Started | High | 0 | Green
AGI-02 | Agile Product Model | 0-30 Foundation | Assess current work intake, prioritization, funding, release and governance practices | IBM Agile Coach | Horizon PMO / Portfolio | 46208 | 46217 | 10 | AGI-01 | Current-state assessment | Pain points and change impacts documented | Not Started | High | 0 | Green
AGI-03 | Agile Product Model | 0-30 Foundation | Define product/value-stream taxonomy and map applications to candidate product domains | IBM Product Engineering Lead | Horizon Product Owners | 46211 | 46222 | 12 | AGI-01 | Domain/product map | Product domains and ownership draft | Not Started | High | 0 | Green
AGI-04 | Agile Product Model | 0-30 Foundation | Identify first-wave agile enhancement projects and pilot product stream | IBM Transformation Lead | Horizon Product Owners | 46215 | 46224 | 10 | AGI-02;AGI-03 | Pilot product stream selection | Pilot selected and leadership approved | Not Started | High | 0 | Green
AGI-05 | Agile Product Model | 0-30 Foundation | Define product roles, RACI, POD composition, scrum ceremonies and decision rights | IBM Agile Coach | Horizon Product Owners | 46218 | 46232 | 15 | AGI-04 | POD operating model | Roles and decision rights clear | Not Started | High | 0 | Green
AGI-06 | Agile Product Model | 0-30 Foundation | Create pilot backlog foundation with epics, features, stories, acceptance criteria and KPIs | IBM Product Owner Coach | Horizon Product Owner | 46223 | 46234 | 12 | AGI-04;AGI-05 | Pilot backlog | Backlog ready for sprint planning | Not Started | High | 0 | Green
AGI-07 | Agile Product Model | 0-30 Foundation | Train pilot PODs on agile ways of working, product mindset and outcome-based metrics | IBM Agile Coach | Horizon POD Members | 46228 | 46237 | 10 | AGI-05;AGI-06 | Training completion | Pilot team trained and ready | Not Started | High | 0 | Green
AGI-08 | Agile Product Model | 31-60 Production Ready | Launch sprint 0 for pilot POD including tooling, definition of ready/done and release plan | IBM Scrum Master | Horizon Product Owner | 46234 | 46243 | 10 | AGI-06;AGI-07 | Sprint 0 readiness | Team ready for sprint execution | Not Started | High | 0 | Green
AGI-09 | Agile Product Model | 31-60 Production Ready | Execute pilot sprint 1-2 with coaching, demos, retrospectives and dependency management | IBM Scrum Master | Horizon Product Owner | 46243 | 46262 | 20 | AGI-08 | Pilot sprint outcomes | Velocity, impediments and demo feedback captured | Not Started | High | 0 | Green
AGI-10 | Agile Product Model | 31-60 Production Ready | Establish product metrics dashboard: velocity, predictability, backlog health, value and quality | IBM Transformation Office | Horizon PMO | 46253 | 46262 | 10 | AGI-08;AGI-09 | Product metrics dashboard | Metrics visible for pilot POD | Not Started | High | 0 | Green
AGI-11 | Agile Product Model | 61-90 Standardize & Integrate | Standardize intake and prioritization workflow across pilot products and AMS requests | IBM Product Transformation Lead | Horizon Portfolio Lead | 46264 | 46283 | 20 | AGI-09;AGI-10 | Standard intake workflow | Demand routed and prioritized by value | Not Started | High | 0 | Green
AGI-12 | Agile Product Model | 61-90 Standardize & Integrate | Scale agile ceremonies and product backlog model to next-wave PODs | IBM Agile Coach | Horizon Product Owners | 46268 | 46292 | 25 | AGI-09;AGI-11 | Next-wave POD setup | Additional PODs operating with common cadence | Not Started | High | 0 | Green
AGI-13 | Agile Product Model | 61-90 Standardize & Integrate | Integrate DevSecOps 2.0 practices and quality gates into pilot / cloud app PODs | IBM DevSecOps Lead | Horizon DevOps Lead | 46278 | 46292 | 15 | AGI-08;AGI-12 | DevSecOps adoption plan | Pipeline gates and security checks embedded | Not Started | High | 0 | Green
AGI-14 | Agile Product Model | 61-90 Standardize & Integrate | Conduct 90-day product model health review and refine operating model | IBM Product Transformation Lead | Horizon Executive Sponsor | 46293 | 46312 | 20 | AGI-10;AGI-12;AGI-13 | 90-day health review | Model refinements approved | Not Started | High | 0 | Green
AGI-15 | Agile Product Model | 91-180 Scale & Optimize | Expand product/value-stream governance into monthly portfolio and quarterly value reviews | IBM Transformation Office | Horizon PMO | 46294 | 46323 | 30 | AGI-14 | Product governance cadence | Roadmap, value and capacity reviews live | Not Started | High | 0 | Green
AGI-16 | Agile Product Model | 91-180 Scale & Optimize | Build product roadmaps for priority domains covering BAU, tech debt and transformation items | IBM Product Owners / Coaches | Horizon Product Owners | 46303 | 46337 | 35 | AGI-11;AGI-15 | Product roadmaps | Domain roadmaps aligned to business outcomes | Not Started | High | 0 | Green
AGI-17 | Agile Product Model | 91-180 Scale & Optimize | Embed innovation sprint cadence and market/payer trend backlog intake | IBM Transformation Lead | Horizon Product Owners | 46318 | 46347 | 30 | AGI-15;AGI-16 | Innovation sprint model | Quarterly innovation intake live | Not Started | High | 0 | Green
AGI-18 | Agile Product Model | 91-180 Scale & Optimize | Optimize POD capacity model, talent rotation and skill evolution for AI/cloud/data needs | IBM Delivery Lead | Horizon Resource Owners | 46333 | 46357 | 25 | AGI-12;AGI-16 | Capacity and skill roadmap | Talent rotation plan tied to roadmap | Not Started | High | 0 | Green
AGI-19 | Agile Product Model | 91-180 Scale & Optimize | Complete 180-day agile/product maturity assessment and scale roadmap | IBM Product Transformation Lead | Horizon Executive Sponsor | 46353 | 46382 | 30 | AGI-16;AGI-18 | Agile/product scale roadmap | Maturity delta and scale roadmap approved | Not Started | High | 0 | Green
Formulas:
RAG = IF([Status]="Completed","Green",IF(TODAY()>[End Date],"Red",IF(AND(TODAY()+14>[End Date],O2<0.75),"Amber","Green")))

## RAID & Dependencies
Type | ID | Description | Impacted Workstream | Owner | Dependency / Trigger | Target Resolution | Status | Mitigation / Next Step
Dependency | D-01 | ARB/security approval required for AIOps and CareOps360 environments | AIOps / CareOps360 | Horizon ARB / Security | Architecture packages and security review | 2026-07-15 | Open | Package MVP and target-state approvals separately to accelerate foundation
Dependency | D-02 | Source-system owners must provide access and data contracts for CareOps360 feeds | CareOps360 | Horizon Source Owners | ServiceNow, APM, Databricks, contact center, provider data | 2026-08-31 | Open | Create source readiness tracker with owners and escalation path
Dependency | D-03 | Historical ITSM ticket quality and taxonomy affects AIOps model accuracy | AIOps | IBM AIOps Data Lead / Horizon ITSM | Historical incidents, categories, assignment groups, resolutions | 2026-07-31 | Open | Cleanse taxonomy and curate knowledge corpus during first 60 days
Risk | R-01 | QE automation scale may be limited by test data availability or external dependency instability | Quality Engineering | IBM QE Lead / Horizon Data Owner | TDM, masking, synthetic data, service virtualization | 2026-09-15 | Open | Prioritize critical flows; stand up TDM intake and virtualize high-pain dependencies
Risk | R-02 | Product model adoption may stall without dedicated Horizon product owners and SMEs | Agile Product Model | Horizon Executive Sponsor | Product owner / SME commitment | 2026-07-30 | Open | Agree minimum capacity commitment and cadence in governance
Assumption | A-01 | Initial 180-day plan begins July 1, 2026 and covers calendar days through late December 2026 | All | IBM Transformation Office | Start-date confirmation | 2026-07-01 | Open | Adjust dates if contract transition start changes
Issue | I-01 | Tooling integration priorities may change based on ClearQuest-to-ServiceNow migration timing | AIOps / Overall Transition | Horizon ITSM Lead | ITSM migration roadmap | 2026-08-15 | Open | Design interfaces to support interim and target ITSM paths
Decision | DEC-01 | Confirm first product pilot and first 5 AWS applications for AIOps onboarding | AIOps / Agile Product Model | Horizon Product Owners | Pilot selection workshop | 2026-07-10 | Open | Decision needed to protect 0-30 day foundation timeline

## RACI & Owners
Area | Accountable IBM Owner | Primary Horizon Owner | Key Responsibilities | Primary Cadence | Key Decisions / Escalations
Overall Transition | IBM Transformation Lead / Delivery Lead | Horizon Executive Sponsor / PMO | Own 180-day transition execution, governance, risks, service continuity and transition acceptance | Daily standup, weekly ops, monthly exec | Scope, resource blockers, SLA impact, acceptance
Quality Engineering | IBM QE Lead / QE Architect | Horizon QA Lead / Business SMEs | Define QE strategy, automation roadmap, TDM, service virtualization, defect analytics and release readiness | Weekly QE working session, monthly quality review | Automation scope, critical flows, quality gates, UAT support model
AIOps Implementation | IBM AIOps Program Manager / AIOps Architect | Horizon ARB, ITSM and Operations Leads | Deploy AIOps foundation, integrate ITSM/monitoring, train models, scale recommendations and auto-remediation | Weekly AIOps delivery, monthly operations review | ARB/security approvals, tool integrations, guardrails, automation candidates
CareOps360 | CareOps360 Product Owner / Architect | Horizon Transformation Sponsor / Data Owners | Enable executive command-center dashboards, data integrations, AI insights, write-back workflows and adoption | Weekly product review, monthly dashboard playback | Data access, ARB approvals, persona priorities, write-back controls
Agile Product Model | IBM Product Transformation Lead / Agile Coach | Horizon Product Owners / PMO | Shift to product/value-stream PODs, agile ceremonies, intake, metrics, roadmaps and innovation cadence | Sprint ceremonies, monthly portfolio review | Pilot selection, domain model, capacity, product KPIs

## Lookups
Status | Owners / Stakeholders
Not Started | CareOps360 AI Lead
In Progress | CareOps360 Architect
Blocked | CareOps360 Change Lead
At Risk | CareOps360 Data Lead
Completed | CareOps360 Engineering Lead
CareOps360 Product Owner
Priority | Horizon ARB / Security
Critical | Horizon App Owners
High | Horizon Business Owners
Medium | Horizon Business SMEs
Low | Horizon Data / Integration
Horizon Data Owner
RAG | Horizon DevOps Lead
Green | Horizon Domain Owners
Amber | Horizon Executive Sponsor
Red | Horizon ITSM / Jira Owners
Horizon ITSM Lead
Workstream | Horizon Infrastructure Lead
Overall Transition | Horizon Integration Lead
Quality Engineering | Horizon Monitoring Lead
AIOps Implementation | Horizon NFR Owners
CareOps360 | Horizon Operations Lead
Agile Product Model | Horizon Operations SMEs
Horizon PMO
Horizon PMO / Portfolio
Horizon POD Members
Horizon Platform Lead
Horizon Portfolio Lead
Horizon Product Owner
Horizon Product Owners
Horizon QA Lead
Horizon Release Manager
Horizon Resource Owners
Horizon Risk / Compliance
Horizon Risk / Security
Horizon SMEs
Horizon Security / ITSM
Horizon Security / Operations
Horizon Security / Release
Horizon Source Owners
Horizon Stakeholders
Horizon Tooling Lead
Horizon Transformation Office
Horizon Transformation Sponsor
IBM AIOps Architect
IBM AIOps Data Lead
IBM AIOps Data Scientist
IBM AIOps Lead
IBM AIOps Program Manager
IBM Agile Coach
IBM App Leads
IBM Delivery Lead
IBM DevSecOps Lead
IBM ITSM Integration Lead
IBM Knowledge Manager
IBM Observability Lead
IBM Product Engineering Lead
IBM Product Owner Coach
IBM Product Owners / Coaches
IBM Product Transformation Lead
IBM QE Analyst
IBM QE Architect
IBM QE Automation Lead
IBM QE Factory Lead
IBM QE Lead
IBM SRE / Ops Lead
IBM SRE Lead
IBM Scrum Master
IBM Service Delivery Manager
IBM TDM Lead
IBM Transformation Lead
IBM Transformation Office
IBM Transition Manager